🧱 Job Board Platform Agile Project Plan — Laravel + React 6 Sprints • ~12 Weeks • Full Stack

📌  Project Overview

A full-stack job board where employers post jobs, admins approve them, and candidates search and apply. Built with Laravel (API) + React (frontend).

| Project | Job Board Platform |
| --- | --- |
| Stack | Laravel 11 (API) + React + Vite (Frontend) |
| Auth | Laravel Sanctum (token-based) |
| Total Sprints | 6 Sprints (+ Sprint 0 Setup) |
| Sprint Length | 2 Weeks per Sprint |
| Estimated Duration | ~12–14 Weeks |
| Team Size | 1 Developer (You) |

👤  User Roles at a Glance

| Role | Can Do | Cannot Do | Sprint Introduced |
| --- | --- | --- | --- |
| Employer | Register, post/edit jobs, review applications | Approve own jobs, access admin panel | Sprint 1 & 2 |
| Candidate | Register, search jobs, apply, manage profile | Post jobs, access employer/admin areas | Sprint 1 & 4 |
| Admin | Approve/reject jobs, monitor platform | Apply for jobs, post as employer | Sprint 3 |

🗓️  Sprint Overview

| # | Sprint Name | Main Deliverable | Weeks | Points | Hours Est. |
| --- | --- | --- | --- | --- | --- |
| 0 | Project Setup | DB schema, Laravel + React boilerplate | Wk 1 | 8 | 10 |
| 1 | Authentication | Register/login for all 3 roles + guards | Wk 2–3 | 21 | 28 |
| 2 | Job Listings (Employer) | Full CRUD for job posts + company logo upload | Wk 4–5 | 26 | 32 |
| 3 | Admin Panel | Approve/reject jobs + activity monitor | Wk 6–7 | 18 | 22 |
| 4 | Candidate Experience | Search, filter, apply, manage applications | Wk 8–9 | 28 | 36 |
| 5 | Application Management | Employer reviews apps, accept/reject flow | Wk 10–11 | 20 | 26 |
| 6 | Polish & Bonus | Responsive UI, notifications, testing | Wk 12–14 | 22 | 30 |

Sprint 0: Project Setup & Architecture 📅 Week 1 (2–3 days) 🎯 Goal: Get Laravel API and React frontend talking to each other with proper folder structure

| ID | Task | Role | Priority | Est. (hrs) | Story Points |
| --- | --- | --- | --- | --- | --- |
| S0-1 | Design full database schema (ERD) — users, jobs, applications tables | Backend | High | 3h | 3 |
| S0-2 | Initialize Laravel 11 project, install Sanctum, configure CORS | Backend | High | 2h | 2 |
| S0-3 | Create all migrations: users, employers, candidates, jobs, applications | Backend | High | 2h | 2 |
| S0-4 | Initialize React + Vite project, install Axios, React Router, TailwindCSS | Frontend | High | 1.5h | 1 |
| S0-5 | Set up project folder structure (feature-based for both projects) | Both | Medium | 1h | 1 |
| S0-6 | Test Laravel ↔ React connection with a /api/ping test endpoint | Both | Medium | 0.5h | 1 |

✅ Done when:

- ERD is drawn and reviewed

- Migrations run successfully (php artisan migrate)

- React dev server can call a Laravel API endpoint and get a response

Sprint 1: Authentication & Role System 📅 Weeks 2–3 🎯 Goal: All 3 user types can register, login, and be redirected to their correct dashboard

| ID | Task | Role | Priority | Est. (hrs) | Story Points |
| --- | --- | --- | --- | --- | --- |
| S1-1 | Create User model with role field (employer / candidate / admin) | Backend | High | 1h | 1 |
| S1-2 | Employer registration API + validation (POST /api/register/employer) | Backend | High | 2h | 2 |
| S1-3 | Candidate registration API + validation (POST /api/register/candidate) | Backend | High | 2h | 2 |
| S1-4 | Login API returning Sanctum token (POST /api/login) | Backend | High | 2h | 2 |
| S1-5 | Logout API + token revocation (POST /api/logout) | Backend | High | 1h | 1 |
| S1-6 | Route middleware: auth:sanctum + role guards (isEmployer, isAdmin, etc.) | Backend | High | 2h | 3 |
| S1-7 | React: Employer Register form with validation | Frontend | High | 3h | 2 |
| S1-8 | React: Candidate Register form with validation | Frontend | High | 3h | 2 |
| S1-9 | React: Login page — stores token in context/localStorage | Frontend | High | 3h | 2 |
| S1-10 | React: Auth context + protected routes (PrivateRoute component) | Frontend | High | 3h | 3 |
| S1-11 | React: Redirect after login based on role (3 different dashboards) | Frontend | Medium | 2h | 1 |
| S1-12 | Employer & Candidate profile page (view + edit own info) | Both | Medium | 4h | 2 |

✅ Done when:

- Employer can register → login → see employer dashboard

- Candidate can register → login → see candidate dashboard

- Unauthenticated users can't access protected pages

- Wrong roles can't access other dashboards

Sprint 2: Job Listings — Employer Side 📅 Weeks 4–5 🎯 Goal: Employers can create, edit, and manage their job postings

| ID | Task | Role | Priority | Est. (hrs) | Story Points |
| --- | --- | --- | --- | --- | --- |
| S2-1 | Job model + migration (title, description, salary, location, work_type, deadline, status, category) | Backend | High | 1.5h | 2 |
| S2-2 | API: Create job listing (POST /api/jobs) — status defaults to "pending" | Backend | High | 2h | 2 |
| S2-3 | API: Edit job listing (PUT /api/jobs/{id}) — employer only | Backend | High | 1.5h | 2 |
| S2-4 | API: Delete job listing (DELETE /api/jobs/{id}) | Backend | High | 1h | 1 |
| S2-5 | API: Get employer's own jobs (GET /api/employer/jobs) | Backend | High | 1h | 1 |
| S2-6 | File upload: company logo via Storage (public disk) | Backend | Medium | 2h | 2 |
| S2-7 | Form Request validation class for job creation | Backend | Medium | 1h | 1 |
| S2-8 | React: Create Job form (all fields from spec) | Frontend | High | 4h | 3 |
| S2-9 | React: Edit Job form (pre-filled from API) | Frontend | High | 3h | 2 |
| S2-10 | React: Employer job listings table with status badges (Pending / Approved / Rejected) | Frontend | High | 3h | 3 |
| S2-11 | React: Logo upload component with preview | Frontend | Medium | 2h | 2 |
| S2-12 | React: Delete job with confirmation modal | Frontend | Medium | 1.5h | 1 |
| S2-13 | API Resources: JobResource for consistent JSON shape | Backend | Low | 1h | 1 |

✅ Done when:

- Employer can fill a form and post a job (status = Pending)

- Employer sees all their jobs with correct status indicators

- Employer can edit and delete their own jobs

- Logo uploads and displays correctly

Sprint 3: Admin Panel — Approval Flow 📅 Weeks 6–7 🎯 Goal: Admins can review and approve/reject job postings before they go live

| ID | Task | Role | Priority | Est. (hrs) | Story Points |
| --- | --- | --- | --- | --- | --- |
| S3-1 | API: Get all pending jobs (GET /api/admin/jobs?status=pending) | Backend | High | 1.5h | 2 |
| S3-2 | API: Approve job (PATCH /api/admin/jobs/{id}/approve) | Backend | High | 1h | 2 |
| S3-3 | API: Reject job with reason (PATCH /api/admin/jobs/{id}/reject) | Backend | High | 1.5h | 2 |
| S3-4 | API: Dashboard stats — total users, jobs, applications counts | Backend | Medium | 2h | 2 |
| S3-5 | API: List all users with filtering (GET /api/admin/users) | Backend | Medium | 1.5h | 2 |
| S3-6 | React: Admin dashboard with stat cards (jobs pending, total users, etc.) | Frontend | High | 3h | 2 |
| S3-7 | React: Jobs approval table — view details, approve, reject with reason | Frontend | High | 4h | 3 |
| S3-8 | React: Users list table (read-only monitoring) | Frontend | Medium | 2h | 1 |
| S3-9 | React: Job detail modal/preview for admin before approving | Frontend | Medium | 2h | 2 |

✅ Done when:

- Admin sees all pending jobs in a table

- Admin can click Approve → job becomes visible to candidates

- Admin can click Reject + add a reason → employer sees rejection

- Admin dashboard shows real platform stats

Sprint 4: Candidate Experience — Search & Apply 📅 Weeks 8–9 🎯 Goal: Candidates can discover jobs and submit applications

| ID | Task | Role | Priority | Est. (hrs) | Story Points |
| --- | --- | --- | --- | --- | --- |
| S4-1 | API: List approved jobs with filters (keyword, location, category, salary, date, experience) | Backend | High | 3h | 3 |
| S4-2 | API: Single job detail page (GET /api/jobs/{id}) | Backend | High | 1h | 1 |
| S4-3 | Application model + migration (job_id, candidate_id, resume, status, notes) | Backend | High | 1h | 1 |
| S4-4 | API: Submit application with resume upload (POST /api/jobs/{id}/apply) | Backend | High | 2.5h | 3 |
| S4-5 | API: Apply via contact info only (returns employer email/phone) | Backend | Medium | 1.5h | 2 |
| S4-6 | API: Candidate's own applications list (GET /api/candidate/applications) | Backend | High | 1h | 1 |
| S4-7 | API: Cancel application (DELETE /api/applications/{id}) | Backend | High | 1h | 1 |
| S4-8 | React: Job listings page with search bar + filter sidebar | Frontend | High | 5h | 5 |
| S4-9 | React: Job detail page (full info + Apply button) | Frontend | High | 3h | 2 |
| S4-10 | React: Apply modal — choose resume upload or contact info | Frontend | High | 3h | 3 |
| S4-11 | React: My Applications page — list with status + cancel button | Frontend | High | 3h | 2 |
| S4-12 | Prevent duplicate applications (unique constraint + API check) | Backend | Medium | 1h | 1 |
| S4-13 | React: Pagination component for job listings | Frontend | Medium | 2h | 2 |

✅ Done when:

- Candidate can search + filter the approved jobs listing

- Candidate can open a job detail and click Apply

- Application is saved with resume OR contact info route works

- Candidate sees their applications list and can cancel one

Sprint 5: Application Management — Employer Side 📅 Weeks 10–11 🎯 Goal: Employers can review all applications for their jobs and respond

| ID | Task | Role | Priority | Est. (hrs) | Story Points |
| --- | --- | --- | --- | --- | --- |
| S5-1 | API: Get applications for employer's jobs (GET /api/employer/applications) | Backend | High | 1.5h | 2 |
| S5-2 | API: Accept application (PATCH /api/applications/{id}/accept) | Backend | High | 1h | 2 |
| S5-3 | API: Reject application (PATCH /api/applications/{id}/reject) | Backend | High | 1h | 2 |
| S5-4 | API: Download candidate resume (GET /api/applications/{id}/resume) | Backend | High | 1.5h | 2 |
| S5-5 | React: Applications inbox — organized by job listing | Frontend | High | 4h | 3 |
| S5-6 | React: Applicant card — name, resume download, accept/reject buttons | Frontend | High | 3h | 3 |
| S5-7 | React: Status updates reflect immediately (optimistic update or refetch) | Frontend | Medium | 2h | 2 |
| S5-8 | Candidate sees updated application status (Pending / Accepted / Rejected) | Frontend | High | 1h | 1 |
| S5-9 | API Tests: write basic Feature tests for auth + job + application endpoints | Backend | Medium | 4h | 3 |

✅ Done when:

- Employer sees all applicants grouped by their job posts

- Employer can download resumes and accept/reject applicants

- Candidate's application status updates accordingly

- Core API endpoints have passing tests

Sprint 6: Polish, Responsiveness & Bonus Features 📅 Weeks 12–14 🎯 Goal: Platform is production-ready, responsive, and delightful to use

| ID | Task | Role | Priority | Est. (hrs) | Story Points |
| --- | --- | --- | --- | --- | --- |
| S6-1 | Full mobile responsiveness audit + fixes (all pages) | Frontend | High | 6h | 3 |
| S6-2 | Consistent design system — spacing, colors, typography | Frontend | High | 4h | 2 |
| S6-3 | Loading states, skeleton screens, error boundaries | Frontend | Medium | 3h | 2 |
| S6-4 | Toast notifications (success, error, info) across all actions | Frontend | Medium | 2h | 1 |
| S6-5 | BONUS: Email notifications (Laravel Mail + Queue) — new application alert | Backend | Low | 4h | 3 |
| S6-6 | BONUS: In-app notifications (Bell icon + unread count) | Both | Low | 5h | 3 |
| S6-7 | BONUS: Employer resume database search (search candidates by skill) | Backend | Low | 3h | 2 |
| S6-8 | BONUS: Share job to social media (open graph meta tags) | Frontend | Low | 2h | 1 |
| S6-9 | Final end-to-end manual QA pass — all 3 user roles | Both | High | 4h | 3 |
| S6-10 | README documentation + API endpoint reference | Both | Medium | 2h | 2 |

✅ Done when:

- Platform works correctly on mobile and desktop

- Every action has feedback (loading / success / error)

- All 3 roles can complete their full user journey without bugs

🛠️  Tech Stack Quick Reference

| Layer | Technology | Key Package | Purpose |
| --- | --- | --- | --- |
| API | Laravel 11 | laravel/sanctum | Auth tokens + API |
| Database | MySQL | Eloquent ORM | Data persistence |
| File Storage | Laravel Storage | Intervention/Image | Logos + resumes |
| Frontend | React + Vite | React Router v6 | SPA routing |
| HTTP Client | Axios | react-query (opt.) | API calls + caching |
| Styling | Tailwind CSS | headlessui/react | UI components |
| Validation | Form Requests | Zod (frontend) | Input validation |
| Testing | PHPUnit | Pest (optional) | API feature tests |

💡  Pro Tips for Solo Building

🔑 Build the backend API first, test it in Postman or Hoppscotch, THEN connect the frontend.

🗄️ Never skip migrations — always use them. Direct DB edits will haunt you.

🔒 Get auth + role middleware right in Sprint 1. Everything else depends on it.

📬 Use Laravel API Resources from Sprint 2 — consistent JSON structure saves frontend pain.

🧪 Test each Sprint's API in Postman before writing the React code.

🎨 Use a UI component library (shadcn/ui or Headless UI + Tailwind) — it'll save 30% of time.

🚫 Don't build bonus features until Sprints 1–5 are working end-to-end.

You've got this. Sprint 0 starts now. 🚀